## Feuille1
Project Schedule – PIL Discrete choices in Bike Sharing Transportation System
	Task	Done	Estimated Time	Real Time	Deadline	Remarks
General	Organisation	-	?	2
	Meetings	-	?	1
				3	-

Biblio	Documentation on Vlib		1
	Statistical analyses and datamining		2	2
	Discrete choices models ?		2
	Biblio Synthesis population		1
	Write Bibliographic report		2
			8	2	30/03/14

Development	Brainstorming for Questionnaire	X	1	1
	Detailed elaboration of questionnaire		4
	Writing of pilote questionnaire		2
	Coding of flexible Platform / database		8
			15	1	15/04/14

Enquete	Field work		8			+ more time not during work hours
	Data export and cleaning		2
			10		15/05/14	One entire month because need test of pilote questionnaire, revision, etc

Modelling	Formalisation of discrete choice models		2
	Calibration and estimation on data		2
	Analysis and synthesis of results (written report)		4
	Population synthetisation in ABM		2
	Discrete choice in ABM		2
	Calibration of ABM, use of calibrated model		2
	Analysis of ABM results		4
			18		10/06/14

Writing	Gathering already written part		2
	Report for pil		12		20/06/14
	Writing the paper		?		15/07/14